**ORDINANCE NO. 21-2021**

**AUTHORIZING THE VILLAGE ADMINISTRATOR TO EXECUTE A CHANGE ORDER FOR THE 2020 RESIDENTIAL STREET PAVING PROJECT AND DECLARING AN EMERGENCY**

**WHEREAS**, this Council previously passed Ordinance No. 17-2020, awarding a contract to the JK Meurer Construction Company (“JK Meurer”) for the 2020 Residential Street Repaving Project (the “Project”), as supplemented, in the amount of $358,368.50; and

**WHEREAS**, Change Order No. 3 has been submitted and recommended by the Village Engineer for 448 square yards of additional pavement grinding and resurfacing of Spring Street, in the amount of $5,831.00.

**NOW, THEREFORE, BE IT ORDAINED** by the Council of the Village of Fairfax, State of Ohio that:

**SECTION I**: Council hereby approves, and authorizes the Village Administrator to execute, Change Order No. 3 in the amount of $5,831.00, attached hereto as Exhibit A, bringing the total cost of the Project to $364,199.50 and amending the contract for the Project accordingly.

**SECTION II**: This Ordinance is hereby declared to be an emergency measure necessary for the preservation of the public peace, health, safety and general welfare and shall be effective immediately. The reason for said declaration of emergency is the immediate need to approve the additional work items for the Project in order to meet the completion requirement of the contract.

Passed this 21st day of June, 2021.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Mayor

ATTEST:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Fiscal Officer

CERTIFICATE

I hereby certify this to be a true and correct copy of Ordinance No. 21-2021 passed at a meeting of the Council of the Village of Fairfax on this 21st day of June, 2021.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_